## manhours
FPSO PEREGRINO - MANPOWER LOADING
|  | PLANNED TOTAL WEEKLY MANHOURS (Rev.0(B)) | [10 empty] | PLANNED TOTAL WEEKLY MANHOURS (Rev.0(B3)) | [10 empty] | PLANNED TOTAL WEEKLY MANHOURS (Rev.1) | [10 empty] | PLANNED TOTAL WEEKLY MANHOURS (Rev.2C) | [10 empty] | ACTUAL TOTAL WEEKLY MANHOURS
CALENDAR WEEK | DATE (WEEK ENDING) | HULL | MACHINERY | E | C | ELECTRICAL | PIPING | SHIPWRIGHT | OTHERS | WEEKLY TOTAL MANHOURS | CUMULATIVE MANHOURS | REMARK | HULL | MACHINERY | ELECTRICAL | CARPENTER | ELECTRICAL | PIPING | SHIPWRIGHT | OTHERS | WEEKLY TOTAL MANHOURS | CUMULATIVE MANHOURS | REMARK | HULL | MACHINERY | E | C | ELECTRICAL | PIPING | SHIPWRIGHT | OTHERS | WEEKLY TOTAL MANHOURS | CUMULATIVE MANHOURS | REMARK | HULL | MACHINERY | E | C | ELECTRICAL | PIPING | SHIPWRIGHT | OTHERS | WEEKLY TOTAL MANHOURS | CUMULATIVE MANHOURS | REMARK | HULL | MACHINERY | E | C | ELECTRICAL | PIPING | SHIPWRIGHT | OTHERS | WEEKLY TOTAL MANHOURS | CUMULATIVE MANHOURS | REMARK
6 | 2008-02-07
7 | 2008-02-14
8 | 2008-02-21
9 | 2008-02-28
10 | 2008-03-06
11 | 2008-03-13
12 | 2008-03-20
13 | 2008-03-27
14 | 2008-04-03
15 | 2008-04-10
16 | 2008-04-17
17 | 2008-04-24
18 | 2008-05-01
19 | 2008-05-08
20 | 2008-05-15
21 | 2008-05-22
22 | 2008-05-29
23 | 2008-06-05 | [26 empty] | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  | 0
24 | 2008-06-12 | [26 empty] | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  | 0
25 | 2008-06-19 | [26 empty] | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  | 0
26 | 2008-06-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.5 | 45.5 | 45.5 | [5 empty] | 0 |  |  | 40 | 40 | 40 | [5 empty] | 0 |  |  | 40 | 40 | 40 | [5 empty] | 0 |  |  | 40 | 40 | 40 | [5 empty] | 0 |  |  | 40 | 40 | 40
27 | 2008-07-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.6 | 80.6 | 126.1 | [5 empty] | 0 |  |  | 60 | 60 | 100 | [5 empty] | 0 |  |  | 60 | 60 | 100 | [5 empty] | 0 |  |  | 60 | 60 | 100 | [5 empty] | 0 |  |  | 60 | 60 | 100
28 | 2008-07-10 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 69.2 | 87.8 | 213.9 |  | 20 |  |  |  | 0 |  |  | 60 | 80 | 180 |  | 20 |  |  |  | 0 |  |  | 60 | 80 | 180 |  | 20 |  |  |  | 0 |  |  | 60 | 80 | 180 |  | 20 |  |  |  | 0 |  |  | 60 | 80 | 180
29 | 2008-07-17 | 166.1 | 0 | 0 | 0 | 0 | 0 | 0 | 76.9 | 243 | 456.9 |  | 60 |  |  |  | 0 |  |  | 60 | 120 | 300 |  | 60 |  |  |  | 0 |  |  | 60 | 120 | 300 |  | 60 |  |  |  | 0 |  |  | 60 | 120 | 300 |  | 60 |  |  |  | 0 |  |  | 60 | 120 | 300
30 | 2008-07-24 | 309.3 | 0 | 0 | 0 | 0 | 0 | 0 | 63.8 | 373.1 | 830 |  | 60 |  |  |  | 0 |  |  | 60 | 120 | 420 |  | 60 |  |  |  | 0 |  |  | 60 | 120 | 420 |  | 60 |  |  |  | 0 |  |  | 60 | 120 | 420 |  | 60 |  |  |  | 0 |  |  | 60 | 120 | 420
31 | 2008-07-31 | 307.9 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 418.9 | 1248.9 |  | 60 |  |  |  | 0 |  |  | 96 | 156 | 576 |  | 60 |  |  |  | 0 |  |  | 96 | 156 | 576 |  | 60 |  |  |  | 0 |  |  | 96 | 156 | 576 |  | 60 |  |  |  | 0 |  |  | 96 | 156 | 576
32 | 2008-08-07 | 393.8 | 0 | 0 | 0 | 0 | 0 | 0 | 152.3 | 546.1 | 1795 |  | 80 |  |  |  | 0 |  |  | 144 | 224 | 800 |  | 80 |  |  |  | 0 |  |  | 144 | 224 | 800 |  | 80 |  |  |  | 0 |  |  | 144 | 224 | 800 |  | 80 |  |  |  | 0 |  |  | 144 | 224 | 800
33 | 2008-08-14 | 475.9 | 0 | 0 | 0 | 0 | 0 | 0 | 159.6 | 635.5 | 2430.5 |  | 1210 |  |  |  | 0 |  |  | 144 | 1354 | 2154 |  | 1210 |  |  |  | 0 |  |  | 144 | 1354 | 2154 |  | 1210 |  |  |  | 0 |  |  | 144 | 1354 | 2154 |  | 1210 |  |  |  | 0 |  |  | 144 | 1354 | 2154
34 | 2008-08-21 | 989.6 | 0 | 0 | 0 | 0 | 0 | 0 | 188.8 | 1178.4 | 3608.9 |  | 2079 |  |  |  | 0 |  | 154 | 168 | 2401 | 4555 |  | 2079 |  |  |  | 0 |  | 154 | 168 | 2401 | 4555 |  | 2079 |  |  |  | 0 |  | 154 | 168 | 2401 | 4555 |  | 2079 |  |  |  | 0 |  | 154 | 168 | 2401 | 4555
35 | 2008-08-28 | 1573.8 | 0 | 0 | 0 | 0 | 4.9 | 0 | 190.3 | 1769 | 5377.9 |  | 1902 |  |  |  | 0 |  | 213 | 168 | 2283 | 6838 |  | 1902 |  |  |  | 0 |  | 213 | 168 | 2283 | 6838 |  | 1902 |  |  |  | 0 |  | 213 | 168 | 2283 | 6838 |  | 1902 |  |  |  | 0 |  | 213 | 168 | 2283 | 6838
36 | 2008-09-04 | 2146.3 | 0 | 0 | 0 | 0 | 16.6 | 0 | 223.5 | 2386.4 | 7764.3 |  | 3048 |  |  |  | 0 |  | 460 | 200 | 3708 | 10546 |  | 3048 |  |  |  | 0 |  | 460 | 200 | 3708 | 10546 |  | 3048 |  |  |  | 0 |  | 460 | 200 | 3708 | 10546 |  | 3048 |  |  |  | 0 |  | 460 | 200 | 3708 | 10546
37 | 2008-09-11 | 3211.4 | 0 | 0 | 0 | 0 | 21 | 0 | 227.2 | 3459.6 | 11223.9 |  | 4385 |  |  |  | 0 |  | 341 | 224 | 4950 | 15496 |  | 4385 |  |  |  | 0 |  | 341 | 224 | 4950 | 15496 |  | 4385 |  |  |  | 0 |  | 341 | 224 | 4950 | 15496 |  | 4385 |  |  |  | 0 |  | 341 | 224 | 4950 | 15496
38 | 2008-09-18 | 5260.5 | 0 | 0 | 0 | 0 | 19 | 0 | 280.4 | 5559.9 | 16783.8 |  | 4577 |  |  |  | 0 |  | 338 | 224 | 5139 | 20635 |  | 4577 |  |  |  | 0 |  | 338 | 224 | 5139 | 20635 |  | 4577 |  |  |  | 0 |  | 338 | 224 | 5139 | 20635 |  | 4577 |  |  |  | 0 |  | 338 | 224 | 5139 | 20635
39 | 2008-09-25 | 6400.3 | 0 | 0 | 0 | 0 | 8.1 | 0 | 271.5 | 6679.9 | 23463.7 |  | 4015 |  |  |  | 0 |  | 282 | 224 | 4521 | 25156 |  | 4015 |  |  |  | 0 |  | 282 | 224 | 4521 | 25156 |  | 4015 |  |  |  | 0 |  | 282 | 224 | 4521 | 25156 |  | 4015 |  |  |  | 0 |  | 282 | 224 | 4521 | 25156
40 | 2008-10-02 | 8213.8 | 0 | 0 | 0 | 0 | 0.4 | 80 | 423.5 | 8717.7 | 32181.4 |  | 3870 |  |  |  | 0 |  | 237 | 216 | 4323 | 29479 |  | 3870 |  |  |  | 0 |  | 237 | 216 | 4323 | 29479 |  | 3870 |  |  |  | 0 |  | 237 | 216 | 4323 | 29479 |  | 3870 |  |  |  | 0 |  | 237 | 216 | 4323 | 29479
41 | 2008-10-09 | 10140.1 | 16 | 0 | 0 | 0 | 0 | 280 | 749.2 | 11185.3 | 43366.7 |  | 5762 |  |  |  | 0 |  | 590 | 430 | 6782 | 36261 |  | 5762 |  |  |  | 0 |  | 590 | 430 | 6782 | 36261 |  | 5762 |  |  |  | 0 |  | 590 | 430 | 6782 | 36261 |  | 5762 |  |  |  | 0 |  | 590 | 430 | 6782 | 36261
42 | 2008-10-16 | 12222.6 | 56 | 0 | 0 | 0 | 0 | 280 | 832.3 | 13390.9 | 56757.6 |  | 4895 |  |  |  | 0 |  | 707 | 600 | 6202 | 42463 |  | 4895 |  |  |  | 0 |  | 707 | 600 | 6202 | 42463 |  | 4895 |  |  |  | 0 |  | 707 | 600 | 6202 | 42463 |  | 4895 |  |  |  | 0 |  | 707 | 600 | 6202 | 42463 | VESSEL ARRIVED 15/10/08
43 | 2008-10-23 | 15672.5 | 196 | 0 | 0 | 0 | 0 | 280 | 826.6 | 16975.1 | 73732.7 |  | 5042 | 90 |  |  | 130 | 0 | 720 | 820 | 6802 | 49265 |  | 5042 | 90 |  |  | 130 | 0 | 720 | 820 | 6802 | 49265 |  | 5042 | 90 |  |  | 130 | 0 | 720 | 820 | 6802 | 49265 |  | 5042 | 90 |  |  | 130 | 0 | 720 | 820 | 6802 | 49265
44 | 2008-10-30 | 19404.9 | 276 | 0 | 0 | 0 | 0 | 280 | 859 | 20819.9 | 94552.6 |  | 7210 | 386 |  |  | 496 | 240 | 360 | 884 | 9576 | 58841 |  | 7210 | 386 |  |  | 496 | 240 | 360 | 884 | 9576 | 58841 |  | 7210 | 386 |  |  | 496 | 240 | 360 | 884 | 9576 | 58841 |  | 7210 | 386 |  |  | 496 | 240 | 360 | 884 | 9576 | 58841
45 | 2008-11-06 | 22971.3 | 356 | 0 | 0 | 0 | 179.2 | 280 | 859.1 | 24645.6 | 119198.2 |  | 7364 | 140 |  |  | 415 | 480 | 604 | 910 | 9913 | 68754 |  | 7364 | 140 |  |  | 415 | 480 | 604 | 910 | 9913 | 68754 |  | 7364 | 140 |  |  | 415 | 480 | 604 | 910 | 9913 | 68754 |  | 7364 | 140 |  |  | 415 | 480 | 604 | 910 | 9913 | 68754
46 | 2008-11-13 | 25388.3 | 420 | 0 | 0 | 0 | 616 | 280 | 867.4 | 27571.7 | 146769.9 |  | 8662 | 420 |  |  | 1472 | 2010 | 924 | 1020 | 14508 | 83262 |  | 8662 | 420 |  |  | 1472 | 2010 | 924 | 1020 | 14508 | 83262 |  | 8662 | 420 |  |  | 1472 | 2010 | 924 | 1020 | 14508 | 83262 |  | 8662 | 420 |  |  | 1472 | 2010 | 924 | 1020 | 14508 | 83262
47 | 2008-11-20 | 29091.4 | 433.5 | 0 | 0 | 0 | 721.3 | 294.4 | 856.5 | 31397.1 | 178167 |  | 8125 | 560 |  |  | 1774 | 3196 | 2696 | 1060 | 17411 | 100673 |  | 8125 | 560 |  |  | 1774 | 3196 | 2696 | 1060 | 17411 | 100673 |  | 8125 | 560 |  |  | 1774 | 3196 | 2696 | 1060 | 17411 | 100673 |  | 8125 | 560 |  |  | 1774 | 3196 | 2696 | 1060 | 17411 | 100673
48 | 2008-11-27 | 33170.8 | 466.5 | 0 | 0 | 0 | 1444.7 | 404.8 | 938 | 36424.8 | 214591.8 |  | 9280 | 646 |  |  | 1956 | 4018 | 2804 | 1160 | 19864 | 120537 |  | 9280 | 646 |  |  | 1956 | 4018 | 2804 | 1160 | 19864 | 120537 |  | 9280 | 646 |  |  | 1956 | 4018 | 2804 | 1160 | 19864 | 120537 |  | 9280 | 646 |  |  | 1956 | 4018 | 2804 | 1160 | 19864 | 120537
49 | 2008-12-04 | 36278.4 | 640.5 | 93.7 | 0 | 93.7 | 2069.9 | 1471 | 1947.5 | 42501 | 257092.8 |  | 10884 | 631 |  |  | 1668 | 3036 | 2652 | 1410 | 20281 | 140818 |  | 10884 | 631 |  |  | 1668 | 3036 | 2652 | 1410 | 20281 | 140818 |  | 10884 | 631 |  |  | 1668 | 3036 | 2652 | 1410 | 20281 | 140818 |  | 10884 | 631 |  |  | 1668 | 3036 | 2652 | 1410 | 20281 | 140818
50 | 2008-12-11 | 37779.3 | 871.1 | 257.6 | 0 | 257.6 | 3935.7 | 2391.3 | 1971.3 | 47206.3 | 304299.1 |  | 9905 | 646 |  |  | 1347 | 2556 | 1812 | 1409 | 17675 | 158493 |  | 9905 | 646 |  |  | 1347 | 2556 | 1812 | 1409 | 17675 | 158493 |  | 9905 | 646 |  |  | 1347 | 2556 | 1812 | 1409 | 17675 | 158493 |  | 9905 | 646 |  |  | 1347 | 2556 | 1812 | 1409 | 17675 | 158493
51 | 2008-12-18 | 37372.7 | 688.2 | 365.8 | 0 | 365.8 | 5815.2 | 2312.9 | 1966.4 | 48521.2 | 352820.3 |  | 13851 | 1112 |  |  | 1927 | 4957 | 3640 | 1720 | 27207 | 185700 |  | 13851 | 1112 |  |  | 1927 | 4957 | 3640 | 1720 | 27207 | 185700 |  | 13851 | 1112 |  |  | 1927 | 4957 | 3640 | 1720 | 27207 | 185700 |  | 13851 | 1112 |  |  | 1927 | 4957 | 3640 | 1720 | 27207 | 185700
52 | 2008-12-25 | 37733 | 665.7 | 420.7 | 0 | 420.7 | 8109 | 1790 | 1964.6 | 50683 | 403503.3 |  | 13660 | 629 |  |  | 1734 | 3512 | 2817 | 1660 | 24012 | 209712 |  | 13660 | 629 |  |  | 1734 | 3512 | 2817 | 1660 | 24012 | 209712 |  | 13660 | 629 |  |  | 1734 | 3512 | 2817 | 1660 | 24012 | 209712 |  | 13660 | 629 |  |  | 1734 | 3512 | 2817 | 1660 | 24012 | 209712
1 | 2009-01-01 | 39217.1 | 650.5 | 432.2 | 0 | 432.2 | 9498.7 | 1641.2 | 1924.4 | 53364.1 | 456867.4 |  | 13758 | 454 |  |  | 1548 | 4496 | 4148 | 1633 | 26037 | 235749 |  | 13758 | 454 |  |  | 1548 | 4496 | 4148 | 1633 | 26037 | 235749 |  | 13758 | 454 |  |  | 1548 | 4496 | 4148 | 1633 | 26037 | 235749 |  | 13758 | 454 |  |  | 1548 | 4496 | 4148 | 1633 | 26037 | 235749
2 | 2009-01-08 | 40531.9 | 599 | 420 | 0 | 420 | 10635.5 | 2217.5 | 1898.6 | 56302.5 | 513169.9 |  | 16728 | 628 |  |  | 1215 | 5938 | 6098 | 1950 | 32557 | 268306 |  | 16728 | 628 |  |  | 1215 | 5938 | 6098 | 1950 | 32557 | 268306 |  | 16728 | 628 |  |  | 1215 | 5938 | 6098 | 1950 | 32557 | 268306 |  | 16728 | 628 |  |  | 1215 | 5938 | 6098 | 1950 | 32557 | 268306 | Rev.0(B)
3 | 2009-01-15 | 38327.5 | 578.4 | 420 | 0 | 420 | 11692.3 | 2299.9 | 1859 | 55177.1 | 568347 |  | 15690 | 670 | 530 | 0 | 530 | 1730 | 2330 | 1730 | 22680 | 290986 | Rev.0(B3) | 19216 | 348 |  |  | 1317 | 5837 | 4869 | 1872 | 33459 | 301765 |  | 19216 | 348 |  |  | 1317 | 5837 | 4869 | 1872 | 33459 | 301765 |  | 19216 | 348 |  |  | 1317 | 5837 | 4869 | 1872 | 33459 | 301765 | Rev.0(B3)
4 | 2009-01-22 | 34007.1 | 635.6 | 468 | 0 | 468 | 11891 | 2542.9 | 1884.7 | 51429.3 | 619776.3 |  | 19150 | 590 | 700 | 0 | 700 | 1910 | 3060 | 2760 | 28170 | 319156 |  | 23724 | 598 |  |  | 1786 | 5989 | 4081 | 1890 | 38068 | 339833 |  | 23724 | 598 |  |  | 1786 | 5989 | 4081 | 1890 | 38068 | 339833 |  | 23724 | 598 |  |  | 1786 | 5989 | 4081 | 1890 | 38068 | 339833
5 | 2009-01-29 | 29424.5 | 729.9 | 768 | 0 | 768 | 12081 | 3485.9 | 2545.2 | 49034.5 | 668810.8 |  | 22410 | 560 | 430 | 0 | 430 | 2420 | 3920 | 2980 | 32720 | 351876 |  | 14644 | 308 |  |  | 1070 | 4737 | 4565 | 1469 | 26793 | 366626 |  | 14644 | 308 |  |  | 1070 | 4737 | 4565 | 1469 | 26793 | 366626 |  | 14644 | 308 |  |  | 1070 | 4737 | 4565 | 1469 | 26793 | 366626
6 | 2009-02-05 | 27346.6 | 805.9 | 1216 | 57.8 | 1273.8 | 12880 | 5523.9 | 2725.3 | 50555.5 | 719366.3 |  | 26870 | 560 | 420 | 20 | 440 | 3170 | 3540 | 3060 | 37640 | 389516 |  | 21618 | 312 |  |  | 1726 | 6178 | 4611 | 1861 | 36306 | 402932 |  | 21618 | 312 |  |  | 1726 | 6178 | 4611 | 1861 | 36306 | 402932 |  | 21618 | 312 |  |  | 1726 | 6178 | 4611 | 1861 | 36306 | 402932
7 | 2009-02-12 | 24898.4 | 897 | 2196 | 271.4 | 2467.4 | 14604.7 | 8289.1 | 2712.6 | 53869.2 | 773235.5 |  | 30020 | 560 | 420 | 90 | 510 | 3750 | 3570 | 3500 | 41910 | 431426 |  | 20444 | 368 |  |  | 1676 | 6721 | 3674 | 1954 | 34837 | 437769 |  | 20444 | 368 |  |  | 1676 | 6721 | 3674 | 1954 | 34837 | 437769 |  | 20444 | 368 |  |  | 1676 | 6721 | 3674 | 1954 | 34837 | 437769
8 | 2009-02-19 | 25212.2 | 1177.4 | 3012 | 266.8 | 3278.8 | 16662 | 11702.6 | 2713.2 | 60746.2 | 833981.7 |  | 32200 | 430 | 340 | 90 | 430 | 4480 | 3630 | 3540 | 44710 | 476136 |  | 24047 | 326 |  |  | 2008 | 6399 | 5930 | 1920 | 40630 | 478399 |  | 24047 | 326 |  |  | 2008 | 6399 | 5930 | 1920 | 40630 | 478399 |  | 24047 | 326 |  |  | 2008 | 6399 | 5930 | 1920 | 40630 | 478399
9 | 2009-02-26 | 25220.7 | 1178.3 | 4054 | 332 | 4386 | 20579.3 | 13482.2 | 2677.5 | 67524 | 901505.7 |  | 36150 | 320 | 290 | 90 | 380 | 4880 | 4730 | 3200 | 49660 | 525796 |  | 22784 | 436 |  |  | 1976 | 6203 | 6578 | 1930 | 39907 | 518306 |  | 22784 | 436 |  |  | 1976 | 6203 | 6578 | 1930 | 39907 | 518306 |  | 22784 | 436 |  |  | 1976 | 6203 | 6578 | 1930 | 39907 | 518306
10 | 2009-03-05 | 22271.2 | 1568.6 | 5516.1 | 832 | 6348.1 | 22083.5 | 12592.9 | 2634.4 | 67498.7 | 969004.4 |  | 36320 | 210 | 1120 | 300 | 1420 | 6210 | 5590 | 3050 | 52800 | 578596 |  | 30459 | 216 |  |  | 1870 | 8379 | 6578 | 1930 | 49432 | 567738 | ACTUAL | 30459 | 216 |  |  | 1870 | 8379 | 6578 | 1930 | 49432 | 567738 |  | 30459 | 216 |  |  | 1870 | 8379 | 6578 | 1930 | 49432 | 567738
11 | 2009-03-12 | 20640.1 | 1900.1 | 6195.1 | 882 | 7077.1 | 21652 | 8574.2 | 2586.2 | 62429.7 | 1031434.1 |  | 33930 | 130 | 1560 | 340 | 1900 | 7820 | 5540 | 2860 | 52180 | 630776 |  | 28015.2 | 75.6 |  |  | 336 | 5880.8 | 4635.1 | 2797 | 41739.7 | 609477.7 | Rev.1 | 28989 | 196 |  |  | 2296 | 8448 | 6091 | 1930 | 47950 | 615688 |  | 28989 | 196 |  |  | 2296 | 8448 | 6091 | 1930 | 47950 | 615688 | Rev.1
12 | 2009-03-19 | 20269.6 | 2138.2 | 6918.9 | 1026 | 7944.9 | 20379.5 | 4058.7 | 2555.2 | 57346.1 | 1088780.2 |  | 29600 | 160 | 2580 | 360 | 2940 | 9240 | 5330 | 2780 | 50050 | 680826 |  | 23375.2 | 75.6 |  |  | 364.4 | 6561.3 | 4738.9 | 2815.4 | 37930.8 | 647408.5 |  | 33801 | 220 |  |  | 2692 | 9327 | 7398 | 1930 | 55368 | 671056 |  | 33801 | 220 |  |  | 2692 | 9327 | 7398 | 1930 | 55368 | 671056
13 | 2009-03-26 | 18034.9 | 2346.3 | 6772.6 | 1386 | 8158.6 | 20116.8 | 6859.5 | 3005.2 | 58521.3 | 1147301.5 |  | 34470 | 590 | 4180 | 610 | 4790 | 11360 | 8400 | 2750 | 62360 | 743186 |  | 26143.8 | 75.6 |  |  | 476.4 | 6862.5 | 3695 | 2765.8 | 40019.1 | 687427.6 |  | 33908 | 190 |  |  | 2492 | 9830 | 6285 | 2000 | 54705 | 725761 |  | 33908 | 190 |  |  | 2492 | 9830 | 6285 | 2000 | 54705 | 725761
14 | 2009-04-02 | 14308.8 | 1823.2 | 5909.2 | 1623.4 | 7532.6 | 20481.3 | 11577.8 | 3347.6 | 59071.3 | 1206372.8 |  | 42180 | 540 | 5250 | 960 | 6210 | 13490 | 11470 | 2670 | 76560 | 819746 |  | 30857.5 | 75.6 |  |  | 1201.5 | 7307.6 | 4116.7 | 2734.2 | 46293.1 | 733720.7 |  | 35858 | 540 |  |  | 2858 | 10900 | 7153 | 2010 | 59319 | 785080 |  | 35858 | 540 |  |  | 2858 | 10900 | 7153 | 2010 | 59319 | 785080
15 | 2009-04-09 | 13320.7 | 1987.7 | 5433 | 2052 | 7485 | 20160.5 | 17848.7 | 3353 | 64155.6 | 1270528.4 |  | 47520 | 410 | 4560 | 1180 | 5740 | 16090 | 10560 | 2980 | 83300 | 903046 |  | 33891.6 | 135.3 |  |  | 1221.4 | 7593.5 | 3641.1 | 3031.7 | 49514.6 | 783235.3 |  | 33789 | 520 |  |  | 2694 | 9887 | 8057 | 2130 | 57077 | 842157 |  | 33789 | 520 |  |  | 2694 | 9887 | 8057 | 2130 | 57077 | 842157
16 | 2009-04-16 | 11971.6 | 1144.4 | 5206.3 | 2795.6 | 8001.9 | 20428.7 | 23048.8 | 3333.9 | 67929.3 | 1338457.7 |  | 46710 | 490 | 3960 | 1930 | 5890 | 17110 | 6780 | 3460 | 80440 | 983486 |  | 34287.7 | 215.6 |  |  | 1964.3 | 7524.3 | 7365.3 | 3590.1 | 54947.3 | 838182.6 |  | 34665 | 1070 |  |  | 2082 | 8227 | 10918 | 2210 | 59172 | 901329 |  | 34665 | 1070 |  |  | 2082 | 8227 | 10918 | 2210 | 59172 | 901329
17 | 2009-04-23 | 9368.5 | 1977 | 5808.4 | 3297 | 9105.4 | 20544.7 | 29969.6 | 3301.5 | 74266.7 | 1412724.4 |  | 45370 | 540 | 3670 | 2630 | 6300 | 18950 | 3720 | 3380 | 78260 | 1061746 |  | 37367.8 | 200.4 |  |  | 4340.1 | 8842.8 | 12538.8 | 3975.5 | 67265.4 | 905448 |  | 50872 | 1278 |  |  | 3048 | 12860 | 12612 | 2250 | 82920 | 984249 |  | 50872 | 1278 |  |  | 3048 | 12860 | 12612 | 2250 | 82920 | 984249
18 | 2009-04-30 | 8023.2 | 3309.4 | 6671.5 | 3771.9 | 10443.4 | 20081 | 31253.8 | 3274.3 | 76385.1 | 1489109.5 |  | 41770 | 370 | 4110 | 3160 | 7270 | 19230 | 7000 | 3320 | 78960 | 1140706 |  | 39172.8 | 632.7 |  |  | 7523.2 | 10625.6 | 11595.1 | 4062.8 | 73612.2 | 979060.2 |  | 57487 | 1635 |  |  | 3097 | 12973 | 15213 | 2210 | 92615 | 1076864 |  | 57487 | 1635 |  |  | 3097 | 12973 | 15213 | 2210 | 92615 | 1076864
19 | 2009-05-07 | 7025 | 4090 | 9017.7 | 4329 | 13346.7 | 19233.9 | 34800.3 | 3267 | 81762.9 | 1570872.4 |  | 37380 | 920 | 4550 | 3810 | 8360 | 21070 | 14850 | 3300 | 85880 | 1226586 |  | 38270.9 | 987.9 |  |  | 7352.1 | 14376.3 | 4974 | 4042.6 | 70003.8 | 1049064 |  | 51036 | 963 |  |  | 2410 | 10475 | 12421 | 1996 | 79301 | 1156165 |  | 51036 | 963 |  |  | 2410 | 10475 | 12421 | 1996 | 79301 | 1156165
20 | 2009-05-14 | 8452.3 | 3951.3 | 11690.7 | 4947.9 | 16638.6 | 19513.2 | 31740.4 | 3252.3 | 83548.1 | 1654420.5 |  | 35320 | 1390 | 4940 | 4180 | 9120 | 23570 | 19100 | 3290 | 91790 | 1318376 |  | 47664.3 | 1067.7 |  |  | 7613.8 | 17940.1 | 6436.1 | 3968.6 | 84690.6 | 1133754.6 |  | 53292 | 1066 |  |  | 2758 | 11603 | 11370 | 2430 | 82519 | 1238684 |  | 53292 | 1066 |  |  | 2758 | 11603 | 11370 | 2430 | 82519 | 1238684
21 | 2009-05-21 | 9512 | 3534.9 | 14466 | 5637 | 20103 | 20207.5 | 29696.2 | 3226.2 | 86279.8 | 1740700.3 |  | 30980 | 1580 | 5530 | 5320 | 10850 | 26300 | 24400 | 3270 | 97380 | 1415756 |  | 40597.7 | 1122.8 |  |  | 9265.1 | 22428.6 | 16118.1 | 3889.1 | 93421.4 | 1227176 |  | 43297 | 962 |  |  | 2662 | 11519 | 7594 | 2560 | 68594 | 1307278 |  | 43297 | 962 |  |  | 2662 | 11519 | 7594 | 2560 | 68594 | 1307278
22 | 2009-05-28 | 8608.4 | 3501.9 | 16336.2 | 5829 | 22165.2 | 21331.7 | 26742 | 3217.9 | 85567.1 | 1826267.4 |  | 26870 | 1570 | 6570 | 5430 | 12000 | 28020 | 26760 | 3210 | 98430 | 1514186 |  | 34726.3 | 1203.9 |  |  | 10744.5 | 25854.7 | 21760.5 | 3651.9 | 97941.8 | 1325117.8 |  | 49531 | 810 |  |  | 3079 | 14006 | 10303 | 2480 | 80209 | 1387487 |  | 49531 | 810 |  |  | 3079 | 14006 | 10303 | 2480 | 80209 | 1387487
23 | 2009-06-04 | 7952.3 | 3149.6 | 17867.5 | 6069 | 23936.5 | 23848.5 | 21759.7 | 3235.2 | 83881.8 | 1910149.2 |  | 20580 | 1680 | 7740 | 5720 | 13460 | 31430 | 25070 | 3190 | 95410 | 1609596 |  | 29809.2 | 1009.7 |  |  | 11615.1 | 28699.4 | 24405.9 | 3545.2 | 99084.5 | 1424202.3 |  | 43836 | 1024 |  |  | 2803 | 13499 | 10907 | 2790 | 74859 | 1462346 |  | 43836 | 1024 |  |  | 2803 | 13499 | 10907 | 2790 | 74859 | 1462346
24 | 2009-06-11 | 7976.3 | 2847.9 | 18608.4 | 6165 | 24773.4 | 26084.8 | 15907.2 | 3228.1 | 80817.7 | 1990966.9 |  | 16230 | 1950 | 8600 | 5860 | 14460 | 32660 | 15830 | 3200 | 84330 | 1693926 |  | 26590.4 | 2023.1 |  |  | 12244.9 | 30624.3 | 24557.9 | 3509.8 | 99550.4 | 1523752.7 |  | 43741 | 1018 |  |  | 2648 | 13442 | 12546 | 2630 | 76025 | 1538371 |  | 43741 | 1018 |  |  | 2648 | 13442 | 12546 | 2630 | 76025 | 1538371
25 | 2009-06-18 | 7231.1 | 2936.5 | 19190.8 | 6045 | 25235.8 | 29337.9 | 10008.4 | 3253.9 | 78003.6 | 2068970.5 |  | 11190 | 2260 | 10430 | 6060 | 16490 | 32550 | 9080 | 3240 | 74810 | 1768736 |  | 23004.8 | 2793.6 |  |  | 12545.1 | 33069.6 | 25911.1 | 3428.2 | 100752.4 | 1624505.1 |  | 45591 | 1290 |  |  | 3450 | 14125 | 13036 | 2510 | 80002 | 1618373 |  | 45591 | 1290 |  |  | 3450 | 14125 | 13036 | 2510 | 80002 | 1618373
26 | 2009-06-25 | 6202.4 | 2625 | 19251.1 | 5885 | 25136.1 | 30904 | 6763.6 | 3261.1 | 74892.2 | 2143862.7 |  | 8660 | 2780 | 12080 | 6060 | 18140 | 32800 | 14810 | 3250 | 80440 | 1849176 |  | 20179.8 | 1879.1 |  |  | 12918.6 | 34085.6 | 27383.3 | 3425.6 | 99872 | 1724377.1 |  | 41046 | 1360 |  |  | 3467 | 15633 | 14273 | 2679 | 78458 | 1696831 |  | 41046 | 1360 |  |  | 3467 | 15633 | 14273 | 2679 | 78458 | 1696831
27 | 2009-07-02 | 7003.3 | 2581.4 | 20118.8 | 5821 | 25939.8 | 30953.1 | 6161.5 | 3322.1 | 75961.2 | 2219823.9 |  | 6730 | 4100 | 14440 | 6060 | 20500 | 32480 | 17690 | 3240 | 84740 | 1933916 |  | 12186.6 | 2892.1 |  |  | 14691.7 | 34470.2 | 21971.5 | 3371.6 | 89583.7 | 1813960.8 |  | 43055 | 1670 |  |  | 4268 | 17418 | 15949 | 3111 | 85471 | 1782302 |  | 43055 | 1670 |  |  | 4268 | 17418 | 15949 | 3111 | 85471 | 1782302
28 | 2009-07-09 | 7435.3 | 2593.2 | 22408.9 | 5378.1 | 27787 | 31009.5 | 5495.6 | 3338 | 77658.6 | 2297482.5 |  | 6410 | 4770 | 16280 | 6020 | 22300 | 32210 | 27030 | 3240 | 95960 | 2029876 |  | 7031.6 | 5260.6 |  |  | 17284.3 | 33686.2 | 27473.7 | 3325.5 | 94061.9 | 1908022.7 |  | 45932 | 2221 |  |  | 5269 | 19879 | 22538 | 3176 | 99015 | 1881317 |  | 45932 | 2221 |  |  | 5269 | 19879 | 22538 | 3176 | 99015 | 1881317
29 | 2009-07-16 | 7674.6 | 2558.2 | 23912.8 | 4649 | 28561.8 | 31492.4 | 3707.5 | 3327.7 | 77322.2 | 2374804.7 |  | 5520 | 5690 | 18290 | 5400 | 23690 | 31270 | 31980 | 3340 | 101490 | 2131366 |  | 4960.6 | 5854.7 |  |  | 18647.8 | 33270.8 | 32233.5 | 3294 | 98261.4 | 2006284.1 |  | 48705 | 2313 |  |  | 5546 | 22987 | 18587 | 3013 | 101151 | 1982468 |  | 48705 | 2313 |  |  | 5546 | 22987 | 18587 | 3013 | 101151 | 1982468
30 | 2009-07-23 | 7484.5 | 3123.7 | 24689.3 | 4082.1 | 28771.4 | 30059.4 | 2594.8 | 3311.9 | 75345.7 | 2450150.4 |  | 4200 | 5670 | 20060 | 5280 | 25340 | 30040 | 32950 | 3320 | 101520 | 2232886 |  | 5759 | 6617.2 |  |  | 20933.1 | 33415.8 | 33356 | 3332.9 | 103414 | 2109698.1 |  | 44403 | 1655 |  |  | 6603 | 21679 | 18867 | 3247 | 96454 | 2078922 |  | 44403 | 1655 |  |  | 6603 | 21679 | 18867 | 3247 | 96454 | 2078922
31 | 2009-07-30 | 6250.8 | 3723.1 | 25229.3 | 2959 | 28188.3 | 28885.7 | 2590.4 | 3315 | 72953.3 | 2523103.7 |  | 4250 | 5220 | 21320 | 4090 | 25410 | 27260 | 31810 | 3330 | 97280 | 2330166 |  | 3773.9 | 6839.7 |  |  | 21419.1 | 33380.8 | 32261.7 | 3342 | 101017.2 | 2210715.3 |  | 43852 | 2065 |  |  | 7893 | 19197 | 17999 | 3034 | 94040 | 2172962 |  | 43852 | 2065 |  |  | 7893 | 19197 | 17999 | 3034 | 94040 | 2172962
32 | 2009-08-06 | 5362.4 | 3761.5 | 26985.2 | 2473.4 | 29458.6 | 26022.6 | 5185.9 | 3394.5 | 73185.5 | 2596289.2 |  | 5520 | 5080 | 21470 | 3650 | 25120 | 24900 | 27610 | 3370 | 91600 | 2421766 |  | 3072.2 | 6427.1 |  |  | 21812.1 | 31103 | 27687.7 | 3315.6 | 93417.7 | 2304133 |  | 46745 | 2690 |  |  | 7749 | 21634 | 19278 | 2872 | 100968 | 2273930 |  | 46745 | 2690 |  |  | 7749 | 21634 | 19278 | 2872 | 100968 | 2273930
33 | 2009-08-13 | 4047.7 | 3866.2 | 27935.8 | 1432 | 29367.8 | 23913.1 | 2879 | 3392 | 67465.8 | 2663755 |  | 7060 | 4940 | 21560 | 2540 | 24100 | 23420 | 18070 | 3430 | 81020 | 2502786 |  | 3518.4 | 5350.4 |  |  | 22451 | 29681.6 | 17862.8 | 3303.6 | 82167.8 | 2386300.8 |  | 43698 | 2156 |  |  | 7826 | 18628 | 19446 | 2538 | 94292 | 2368222 |  | 43698 | 2156 |  |  | 7826 | 18628 | 19446 | 2538 | 94292 | 2368222
34 | 2009-08-20 | 3801.8 | 3381.1 | 25637.2 | 660.6 | 26297.8 | 21408.5 | 3230.2 | 3391 | 61510.4 | 2725265.4 |  | 6850 | 5510 | 23110 | 1760 | 24870 | 22870 | 5750 | 3460 | 69310 | 2572096 |  | 4208.4 | 4234.8 |  |  | 22432.1 | 27979.1 | 5735.4 | 3377.9 | 67967.7 | 2454268.5 |  | 40887 | 1784 |  |  | 6932 | 21420 | 21241 | 3015 | 95279 | 2463501 |  | 40887 | 1784 |  |  | 6932 | 21420 | 21241 | 3015 | 95279 | 2463501
35 | 2009-08-27 | 3567.9 | 2916.8 | 25841.1 | 304 | 26145.1 | 17974 | 4831 | 3391 | 58825.8 | 2784091.2 |  | 6770 | 4430 | 24830 | 1140 | 25970 | 23570 | 2940 | 3470 | 67150 | 2639246 |  | 5225.9 | 2917.4 |  |  | 22861.4 | 24768.3 | 3012.4 | 3443.7 | 62229.1 | 2516497.6 |  | 51759 | 2406 |  |  | 10875 | 25704 | 24886 | 3184 | 118814 | 2582315 |  | 51759 | 2406 |  |  | 10875 | 25704 | 24886 | 3184 | 118814 | 2582315
36 | 2009-09-03 | 2190.2 | 2556 | 25252.6 | 80 | 25332.6 | 14361.7 | 6462.2 | 3433.3 | 54336 | 2838427.2 |  | 7650 | 4320 | 28850 | 670 | 29520 | 24980 | 2960 | 3500 | 72930 | 2712176 |  | 6933.8 | 2074.7 |  |  | 22363.9 | 23703.3 | 2882.3 | 3440.7 | 61398.7 | 2577896.3 |  | 59927 | 3775 |  |  | 13042 | 28324 | 27260 | 3374 | 135702 | 2718017 |  | 59927 | 3775 |  |  | 13042 | 28324 | 27260 | 3374 | 135702 | 2718017
37 | 2009-09-10 | 2070.5 | 2703.4 | 23084.3 | 0 | 23084.3 | 11681.5 | 7374.6 | 3478 | 50392.3 | 2888819.5 |  | 7170 | 4920 | 29000 | 370 | 29370 | 25620 | 3820 | 3530 | 74430 | 2786606 |  | 6533.5 | 3129.1 |  |  | 20875.9 | 22518.6 | 2890 | 3447.7 | 59394.8 | 2637291.1 |  | 54056 | 4049 |  |  | 13603 | 28553 | 25766 | 3688 | 129715 | 2847732 |  | 54056 | 4049 |  |  | 13603 | 28553 | 25766 | 3688 | 129715 | 2847732
38 | 2009-09-17 | 1726.5 | 2527.1 | 20663.2 | 0 | 20663.2 | 9666.4 | 7414.5 | 3478 | 45475.7 | 2934295.2 |  | 5460 | 4960 | 26390 | 210 | 26600 | 24750 | 5120 | 3590 | 70480 | 2857086 |  | 5832.9 | 3725.7 |  |  | 19203.9 | 20357.3 | 3234.5 | 3535.3 | 55889.6 | 2693180.7 |  | 46421 | 4142 |  |  | 13708 | 28407 | 23207 | 3503 | 119388 | 2967120 |  | 46421 | 4142 |  |  | 13708 | 28407 | 23207 | 3503 | 119388 | 2967120
39 | 2009-09-24 | 1516.2 | 2419.8 | 17281.1 | 0 | 17281.1 | 8910.2 | 6464.1 | 3478 | 40069.4 | 2974364.6 |  | 5530 | 5100 | 22130 | 90 | 22220 | 24540 | 7200 | 3600 | 68190 | 2925276 |  | 6417.4 | 2396 |  |  | 19287.1 | 18641.3 | 5877.4 | 3581 | 56200.2 | 2749380.9 |  | 33461 | 3429 |  |  | 11672 | 24055 | 21185 | 3096 | 96898 | 3064018 |  | 33461 | 3429 |  |  | 11672 | 24055 | 21185 | 3096 | 96898 | 3064018
40 | 2009-10-01 | 1333 | 2507.3 | 13534.1 | 0 | 13534.1 | 7963.6 | 4254.6 | 3482 | 33074.6 | 3007439.2 |  | 5650 | 4850 | 21450 | 90 | 21540 | 23460 | 5610 | 3630 | 64740 | 2990016 |  | 6032 | 2651.7 |  |  | 23061.6 | 19044.9 | 6444 | 3581 | 60815.2 | 2810196.1 |  | 26991 | 3145 |  |  | 12456 | 27271 | 19294 | 3342 | 92499 | 3156517 |  | 26991 | 3145 |  |  | 12456 | 27271 | 19294 | 3342 | 92499 | 3156517
41 | 2009-10-08 | 1324.8 | 2448.1 | 11509.2 | 0 | 11509.2 | 7258.1 | 2995.1 | 3506 | 29041.3 | 3036480.5 |  | 4130 | 4570 | 22120 | 0 | 22120 | 21070 | 3880 | 3630 | 59400 | 3049416 |  | 4975 | 2992 |  |  | 29509 | 18822.2 | 5935.2 | 3633.6 | 65867 | 2876063.1 |  | 29557 | 2856 |  |  | 14014 | 31362 | 22623 | 2916 | 103328 | 3259845 |  | 29557 | 2856 |  |  | 14014 | 31362 | 22623 | 2916 | 103328 | 3259845
42 | 2009-10-15 | 1135.4 | 2878.7 | 10821.1 | 0 | 10821.1 | 6711.5 | 2803.1 | 3506 | 27855.8 | 3064336.3 |  | 3340 | 4050 | 21960 | 0 | 21960 | 18250 | 3450 | 3630 | 54680 | 3104096 |  | 3645.1 | 3469.5 |  |  | 31173.8 | 17812.3 | 4214.9 | 3633.6 | 63949.2 | 2940012.3 |  | 27956 | 2070 |  |  | 13709 | 31591 | 19124 | 3281 | 97731 | 3357576 |  | 27956 | 2070 |  |  | 13709 | 31591 | 19124 | 3281 | 97731 | 3357576
43 | 2009-10-22 | 869.8 | 2718.9 | 8389.2 | 0 | 8389.2 | 5845.4 | 2726.1 | 3513.1 | 24062.5 | 3088398.8 |  | 2490 | 3390 | 22740 | 0 | 22740 | 15740 | 3720 | 3630 | 51710 | 3155806 |  | 3110.3 | 4131.8 |  |  | 27460.4 | 15909.7 | 3791.4 | 3633.6 | 58037.2 | 2998049.5 |  | 24828 | 1583 |  |  | 11092 | 25057 | 14476 | 3616 | 80652 | 3438228 |  | 24828 | 1583 |  |  | 11092 | 25057 | 14476 | 3616 | 80652 | 3438228
44 | 2009-10-29 | 1061.1 | 3227.2 | 8505.8 | 0 | 8505.8 | 4690.1 | 2789.1 | 3574.1 | 23847.4 | 3112246.2 |  | 2080 | 3120 | 24150 | 20 | 24170 | 14100 | 3470 | 3630 | 50570 | 3206376 |  | 2834.6 | 5822.1 |  |  | 23695 | 14384.3 | 3778.5 | 3674.8 | 54189.3 | 3052238.8 |  | 36518 | 3874 |  |  | 13904 | 30963 | 23999 | 3674 | 112932 | 3551160 |  | 36518 | 3874 |  |  | 13904 | 30963 | 23999 | 3674 | 112932 | 3551160
45 | 2009-11-05 | 1433.7 | 3608 | 8449.9 | 0 | 8449.9 | 3983.8 | 2785.1 | 3574.1 | 23834.6 | 3136080.8 |  | 1980 | 3020 | 23740 | 210 | 23950 | 14050 | 4800 | 3630 | 51430 | 3257806 |  | 2837.8 | 4336.3 |  |  | 22024.1 | 13973.6 | 4947.7 | 3686.1 | 51805.6 | 3104044.4 |  | 47324 | 3021 |  |  | 13934 | 31820 | 23044 | 3529 | 122672 | 3673832 |  | 47324 | 3021 |  |  | 13934 | 31820 | 23044 | 3529 | 122672 | 3673832
46 | 2009-11-12 | 2014 | 3550.1 | 8132 | 0 | 8132 | 3275.9 | 2596.9 | 3088.5 | 22657.4 | 3158738.2 |  | 1870 | 3120 | 21770 | 300 | 22070 | 12340 | 5310 | 3630 | 48340 | 3306146 |  | 3507.7 | 2774.4 |  |  | 22114.6 | 15214.9 | 5064.1 | 3686.1 | 52361.8 | 3156406.2 |  | 51237 | 2276 |  |  | 14076 | 29823 | 20200 | 3690 | 121302 | 3795134 |  | 51237 | 2276 |  |  | 14076 | 29823 | 20200 | 3690 | 121302 | 3795134
47 | 2009-11-19 | 2516.2 | 3229.2 | 7369.9 | 0 | 7369.9 | 3040 | 2818.5 | 2790.1 | 21763.9 | 3180502.1 |  | 2040 | 4100 | 21050 | 240 | 21290 | 9380 | 4920 | 3630 | 45360 | 3351506 |  | 2132.7 | 2834 |  |  | 22261.7 | 14504.7 | 4768.5 | 3686.1 | 50187.7 | 3206593.9 |  | 54100 | 2670 |  |  | 14585 | 29465 | 19886 | 3365 | 124071 | 3919205 |  | 54100 | 2670 |  |  | 14585 | 29465 | 19886 | 3365 | 124071 | 3919205
48 | 2009-11-26 | 2575.5 | 2133 | 6345.7 | 0 | 6345.7 | 3213.4 | 2448.7 | 2790.1 | 19506.4 | 3200008.5 |  | 2070 | 3840 | 18250 | 40 | 18290 | 6810 | 3210 | 3480 | 37700 | 3389206 |  | 2060.8 | 2738.5 |  |  | 22084.9 | 12644 | 3462.1 | 3531.1 | 46521.4 | 3253115.3 |  | 40031 | 3040 |  |  | 11520 | 27052 | 18488 | 3888 | 104019 | 4023224 |  | 40031 | 3040 |  |  | 11520 | 27052 | 18488 | 3888 | 104019 | 4023224
49 | 2009-12-03 | 2459.3 | 1603.8 | 6345.2 | 0 | 6345.2 | 3319.7 | 2708.7 | 2795.7 | 19232.4 | 3219240.9 |  | 2130 | 3940 | 14240 | 0 | 14240 | 4990 | 2380 | 2800 | 30480 | 3419686 |  | 2329.3 | 2472.1 |  |  | 20090.7 | 11857.5 | 2502 | 2851.9 | 42103.5 | 3295218.8 |  | 28069 | 2196 |  |  | 14470 | 24211 | 10512 | 2858 | 82316 | 4105540 |  | 28069 | 2196 |  |  | 14470 | 24211 | 10512 | 2858 | 82316 | 4105540
50 | 2009-12-10 | 2587.7 | 1511.8 | 6552.1 | 0 | 6552.1 | 3347 | 2468.7 | 2846.1 | 19313.4 | 3238554.3 |  | 2050 | 3990 | 11650 | 0 | 11650 | 3900 | 2670 | 2800 | 27060 | 3446746 |  | 2659.6 | 2423 |  |  | 18156.8 | 10342.9 | 2947 | 2851.9 | 39381.2 | 3334600 |  | 32343 | 2377 |  |  | 16335 | 28946 | 11114 | 2958 | 94073 | 4199613 |  | 32343 | 2377 |  |  | 16335 | 28946 | 11114 | 2958 | 94073 | 4199613
51 | 2009-12-17 | 1987.3 | 3084.2 | 6704 | 0 | 6704 | 2982.5 | 2498.2 | 2846.1 | 20102.3 | 3258656.6 |  | 2140 | 4200 | 10100 | 0 | 10100 | 3620 | 2840 | 2800 | 25700 | 3472446 |  | 2800.5 | 3841.9 |  |  | 17920.5 | 8821 | 2938 | 2851.9 | 39173.8 | 3373773.8 |  | 29632 | 2266 |  |  | 15010 | 27757 | 13126 | 2763 | 90554 | 4290167 |  | 29632 | 2266 |  |  | 15010 | 27757 | 13126 | 2763 | 90554 | 4290167
52 | 2009-12-24 | 1630 | 3765.7 | 7582 | 0 | 7582 | 2711 | 2596.4 | 2846.1 | 21131.2 | 3279787.8 |  | 2230 | 3750 | 9180 | 0 | 9180 | 3620 | 2730 | 2800 | 24310 | 3496756 |  | 2816.9 | 4314.1 |  |  | 17477.8 | 6853.3 | 2468.5 | 2851.9 | 36782.5 | 3410556.3 |  | 36136 | 2600 |  |  | 15819 | 29163 | 15992 | 2798 | 102508 | 4392675 |  | 36136 | 2600 |  |  | 15819 | 29163 | 15992 | 2798 | 102508 | 4392675
53 | 2009-12-31 | 1817.8 | 5366.7 | 9590 | 0 | 9590 | 2862 | 2679 | 2846.1 | 25161.6 | 3304949.4 |  | 1970 | 3720 | 8430 | 0 | 8430 | 3560 | 2500 | 2800 | 22980 | 3519736 |  | 3740.9 | 3489.1 |  |  | 16039.2 | 5281.4 | 2464.5 | 2851.9 | 33867 | 3444423.3 |  | 30207 | 2336 |  |  | 14342 | 28517 | 13917 | 2696 | 92015 | 4484690 |  | 30207 | 2336 |  |  | 14342 | 28517 | 13917 | 2696 | 92015 | 4484690
1 | 2010-01-07 | 2276.6 | 5969.8 | 10986 | 0 | 10986 | 2936 | 2517.2 | 2550.6 | 27236.2 | 3332185.6 |  | 1580 | 4280 | 7430 | 0 | 7430 | 3760 | 2340 | 2780 | 22170 | 3541906 |  | 2293.8 | 9441.1 |  |  | 13323.1 | 4340.9 | 2464.5 | 2851.9 | 34715.3 | 3479138.6 |  | 34644 | 2406 |  |  | 13587 | 28941 | 13985 | 2717 | 96280 | 4580970 |  | 34644 | 2406 |  |  | 13587 | 28941 | 13985 | 2717 | 96280 | 4580970
2 | 2010-01-14 | 2157.4 | 5494.8 | 10004.5 | 0 | 10004.5 | 4031 | 2029.9 | 1919.1 | 25636.7 | 3357822.3 |  | 1300 | 4250 | 7720 | 0 | 7720 | 3970 | 2190 | 2690 | 22120 | 3564026 |  | 2545.9 | 11790 |  |  | 10977.5 | 4407.1 | 2355.2 | 2779 | 34854.7 | 3513993.3 |  | 4604.7677 | 7179.4822 | 27587.49 | 137.011 | 27724.5011 | 14826.4673 | 12761.9335 | 2113.5871 | 69210.7389 | 4650180.7389 | Rev.2C | 30574 | 2338 |  |  | 12423 | 27831 | 13214 | 3507 | 89887 | 4670857 | Rev. 2C
3 | 2010-01-21 | 1893.4 | 3996.3 | 8347.9 | 0 | 8347.9 | 4452 | 2113.9 | 1919.1 | 22722.6 | 3380544.9 |  | 1300 | 3430 | 7600 | 0 | 7600 | 4010 | 2140 | 2660 | 21140 | 3585166 |  | 5827.2 | 3267.1 |  |  | 10439.8 | 5973.2 | 2320.2 | 2755.6 | 30583.1 | 3544576.4 |  | 7264.3171 | 4744.3811 | 26659.9006 | 239.6717 | 26899.5724 | 29393.6155 | 28130.85 | 3694.3535 | 100127.0895 | 4750307.8284 |  | 62072 | 2526 |  |  | 16079 | 33434 | 17079 | 3427 | 134617 | 4805474
4 | 2010-01-28 | 1360 | 2241.3 | 6346.8 | 0 | 6346.8 | 5311.5 | 2181.2 | 2119.1 | 19559.9 | 3400104.8 |  | 1190 | 1930 | 6920 | 0 | 6920 | 4730 | 1650 | 1920 | 18340 | 3603506 |  | 1730.5 | 2488.9 |  |  | 10524.3 | 9509.6 | 1803.4 | 1968 | 28024.7 | 3572601.1 |  | 5167.7751 | 5471.4633 | 23960.5361 | 239.6717 | 24200.2078 | 28206.5769 | 37558.7184 | 3691.1006 | 104295.8421 | 4854603.6705 |  | 58455 | 2900 |  |  | 15355 | 32670 | 16645 | 3217 | 129242 | 4934716
5 | 2010-02-04 | 864 | 1598.3 | 6078.1 | 0 | 6078.1 | 5979 | 2225.4 | 1919.1 | 18663.9 | 3418768.7 |  | 1120 | 1500 | 7090 | 0 | 7090 | 5420 | 1580 | 1830 | 18540 | 3622046 |  | 949.7 | 2530.6 |  |  | 11928.5 | 12086 | 1970.7 | 1868.9 | 31334.4 | 3603935.5 |  | 4020.0312 | 1380.7797 | 28973.9948 | 68.4405 | 29042.4353 | 38385.0783 | 93144.7315 | 3702.1604 | 169675.2165 | 5024278.887 |  | 35321 | 2904 |  |  | 17167 | 29738 | 22192 | 3406 | 110728 | 5045444
6 | 2010-02-11 | 715.4 | 1513.8 | 7102.1 | 0 | 7102.1 | 5653.5 | 2202 | 1876.9 | 19063.7 | 3437832.4 |  | 740 | 1300 | 6530 | 0 | 6530 | 5740 | 1430 | 1730 | 17470 | 3639516 |  | 761.8 | 2346.7 |  |  | 12172.7 | 11879.5 | 1957.4 | 1811.2 | 30929.3 | 3634864.8 |  | 5049.3705 | 1636.5857 | 22052.6607 | 0 | 22052.6607 | 37963.3758 | 134945.5873 | 3702.5507 | 205350.1307 | 5229629.0177 |  | 26981 | 2966 |  |  | 17073 | 35451 | 28039 | 3641 | 114151 | 5159595
7 | 2010-02-18 | 648.3 | 1424.3 | 7435 | 0 | 7435 | 5460 | 2418.3 | 1832.2 | 19218.1 | 3457050.5 |  | 430 | 1220 | 6060 | 0 | 6060 | 5180 | 1360 | 1690 | 15940 | 3655456 |  | 499.7 | 2183.9 |  |  | 11326 | 10440.4 | 1722 | 1735.2 | 27907.2 | 3662772 |  | 1489.6859 | 1563.331 | 24345.4161 | 0 | 24345.4161 | 42842.2957 | 54849.1723 | 3679.5204 | 128769.4214 | 5358398.4391 |  | 20144 | 2194 |  |  | 13709 | 31184 | 22232 | 2752 | 92215 | 5251810
8 | 2010-02-25 | 643.5 | 1419.5 | 7207 | 4.8 | 7211.8 | 5337.6 | 2441 | 1829.8 | 18883.2 | 3475933.7 |  | 390 | 1220 | 5520 | 0 | 5520 | 4600 | 1360 | 1690 | 14780 | 3670236 |  | 436.4 | 2048.9 |  |  | 9530.1 | 8131.3 | 1457.3 | 1720.2 | 23324.2 | 3686096.2 |  | 1868.3204 | 2348.3144 | 21710.9789 | 0 | 21710.9789 | 49980.011 | 21745.5895 | 3650.8951 | 101304.1093 | 5459702.5484 |  | 20778 | 2057 |  |  | 13715 | 33474 | 21738 | 5027 | 96789 | 5348599
9 | 2010-03-04 | 536.3 | 1312.3 | 6572 | 83.6 | 6655.6 | 4764 | 2451.3 | 1671.2 | 17390.7 | 3493324.4 |  | 390 | 1220 | 4870 | 0 | 4870 | 3900 | 1360 | 1690 | 13430 | 3683666 |  | 436.4 | 1313.9 |  |  | 8902.4 | 5102.6 | 1409.6 | 1720.2 | 18885.1 | 3704981.3 |  | 2368.6124 | 3212.9282 | 17481.5928 | 0 | 17481.5928 | 42955.1054 | 14439.5055 | 3645.17 | 84102.9142 | 5543805.4627 |  | 31097 | 4198 |  |  | 17044 | 48413 | 32910 | 4218 | 137880 | 5486479
10 | 2010-03-11 | 536.3 | 1312.3 | 5891.3 | 318 | 6209.3 | 3732.2 | 1633.8 | 726.2 | 14150.1 | 3507474.5 |  | 240 | 880 | 4280 | 0 | 4280 | 3260 | 1210 | 1600 | 11470 | 3695136 |  | 290.8 | 1081.7 |  |  | 6670.5 | 2660.5 | 1264.1 | 1634.1 | 13601.7 | 3718583 |  | 1906.5742 | 2433.0193 | 13694.077 | 0 | 13694.077 | 32438.5653 | 14396.6977 | 3645.17 | 68514.1035 | 5612319.5662 |  | 26236 | 4638 |  |  | 19202 | 54010 | 40426 | 4975 | 149487 | 5635966
11 | 2010-03-18 | 388.7 | 1016.7 | 4332.3 | 430.5 | 4762.8 | 2498.7 | 1298.7 | 628.3 | 10593.9 | 3518068.4 |  | 110 | 610 | 3000 | 0 | 3000 | 2200 | 1080 | 1520 | 8520 | 3703656 |  | 124.7 | 565.4 |  |  | 3586.3 | 774.4 | 1097.9 | 1667.6 | 7816.3 | 3726399.3 |  | 839.2414 | 2894.0165 | 11471.8439 | 0 | 11471.8439 | 21391.2865 | 14248.757 | 3645.17 | 54490.3153 | 5666809.8814 |  | 15775 | 4126 |  |  | 17754 | 48577 | 33234 | 4074 | 123540 | 5759506
12 | 2010-03-25 | 261.2 | 843 | 2639.4 | 342.6 | 2982 | 1404.8 | 1003.3 | 561.5 | 7055.8 | 3525124.2 |  | 110 | 550 | 1530 | 0 | 1530 | 1040 | 670 | 910 | 4810 | 3708466 |  | 124.7 | 148.7 |  |  | 1747.3 | 265.9 | 690.8 | 990.1 | 3967.5 | 3730366.8 |  | 688.9586 | 5512.1893 | 10006.4895 | 0 | 10006.4895 | 19522.3155 | 14121.3744 | 3645.17 | 53496.4974 | 5720306.3788 |  | 16264 | 4905 |  |  | 19209 | 57727 | 32032 | 4119 | 134256 | 5893762
13 | 2010-04-01 | 261.2 | 603 | 1725.3 | 80.6 | 1805.9 | 1451 | 883.3 | 561.5 | 5565.9 | 3530690.1 |  | 110 | 270 | 1300 | 0 | 1300 | 1130 | 390 | 680 | 3880 | 3712346 |  | 109.7 | 133.7 |  |  | 1900.2 | 22.8 | 387.7 | 484 | 3038.1 | 3733404.9 |  | 1308.3057 | 6248.9001 | 8475.427 | 0 | 8475.427 | 15030.4875 | 15248.2999 | 3644.5195 | 49955.9397 | 5770262.3185 |  | 12452 | 4274 |  |  | 18335 | 52994 | 32265 | 3708 | 124028 | 6017790
14 | 2010-04-08 | 259.2 | 281 | 1352.1 | 0 | 1352.1 | 1182.7 | 743.3 | 560.5 | 4378.8 | 3535068.9 |  | 70 | 90 | 430 | 0 | 430 | 380 | 350 | 460 | 1780 | 3714126 |  | 51.5 | 68.7 |  |  | 619.3 | 0 | 329.6 | 451.5 | 1520.6 | 3734925.5 |  | 2386.5682 | 3862.5921 | 13628.1087 | 0 | 13628.1087 | 8811.5139 | 14847.676 | 3643.2183 | 47179.6772 | 5817441.9957 |  | 10107 | 3356 |  |  | 16870 | 52396 | 31404 | 3199 | 117332 | 6135122
15 | 2010-04-15 | 102.6 | 118.1 | 407.6 | 0 | 407.6 | 228 | 454.6 | 479.1 | 1790 | 3536858.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 410 | 680 | 3714806 |  | 0 | 0 |  |  | 0 | 0 | 278.1 | 417.1 | 695.2 | 3735620.7 |  | 1314.8115 | 1683.6873 | 17448.8038 | 0 | 17448.8038 | 12495.7184 | 12455.2526 | 3643.2183 | 49041.4919 | 5866483.4877 |  | 11589 | 3642 |  |  | 16228 | 52290 | 27156 | 3388 | 114293 | 6249415
16 | 2010-04-22 | 56 | 56 | 73.5 | 0 | 73.5 | 28 | 336 | 448 | 997.5 | 3537856.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 410 | 680 | 3715486 |  | 0 | 0 |  |  | 0 | 0 | 278.1 | 417.1 | 695.2 | 3736315.9 |  | 1200.5706 | 908.5926 | 14037.9708 | 0 | 14037.9708 | 10747.3639 | 13989.8282 | 3643.2183 | 44527.5444 | 5911011.0321 |  | 11756 | 4467 |  |  | 17767 | 53789 | 29986 | 3496 | 121261 | 6370676
17 | 2010-04-29 | 56 | 56 | 56 | 0 | 56 | 28 | 336 | 448 | 980 | 3538836.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 410 | 680 | 3716166 |  | 0 | 0 |  |  | 0 | 0 | 278.1 | 417.1 | 695.2 | 3737011.1 |  | 666.8391 | 897.7931 | 8902.7244 | 0 | 8902.7244 | 9244.2761 | 11284.2182 | 3643.2183 | 34639.0692 | 5945650.1013 |  | 14068 | 4817 |  |  | 19413 | 61217 | 33328 | 3492 | 136335 | 6507011
18 | 2010-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 60 | 100 | 3538936.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 58 | 96 | 3716262 |  | 0 | 0 |  |  | 0 | 0 | 39 | 59 | 98 | 3737109.1 |  | 63.4961 | 110.5977 | 9763.8251 | 0 | 9763.8251 | 5703.7185 | 9740.7948 | 3643.2183 | 29025.6505 | 5974675.7518 |  | 11863 | 4902 |  |  | 17504 | 59663 | 34797 | 3265 | 131994 | 6639005
19 | 2010-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538936.4 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3716262 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 3737109.1 |  | 0 | 71.5632 | 8242.1309 | 0 | 8242.1309 | 2279.4836 | 8652.1231 | 3643.2183 | 22888.5191 | 5997564.2709 |  | 13779 | 4235 |  |  | 17132 | 56964 | 31448 | 3227 | 126785 | 6765790
20 | 2010-05-20 | [31 empty] | 3737109.1 |  | 0 | 71.5632 | 5182.0877 | 0 | 5182.0877 | 1464.5738 | 8510.1677 | 3643.2183 | 18871.6107 | 6016435.8815 |  | 13917 | 4162 |  |  | 15884 | 54340 | 32130 | 3239 | 123672 | 6889462
21 | 2010-05-27 | [33 empty] | 0 | 78.069 | 1317.674 | 0 | 1317.674 | 1640.7494 | 8826.6072 | 3643.2183 | 15506.3179 | 6031942.1994 | [9 empty] | 0
22 | 2010-06-03 | [33 empty] | 0 | 182.1609 | 374.4708 | 0 | 374.4708 | 968.3154 | 9279.5373 | 3643.2183 | 14447.7027 | 6046389.9021 | [9 empty] | 0
23 | 2010-06-10 | [33 empty] | 0 | 104.092 | 40.9862 | 0 | 40.9862 | 65.0575 | 8475.1667 | 4944.3677 | 13629.6701 | 6060019.5722 | [9 empty] | 0
24 | 2010-06-17 | [33 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 5855.1723 | 2602.2988 | 8457.4711 | 6068477.0433 | [9 empty] | 0
25 | 2010-06-24 | [33 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6068477.0433 | [9 empty] | 0
26 | 2010-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538936.4 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3716262 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6068477.0433 | [9 empty] | 0
[10 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0
[24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0